## Sheet1
Finding Type | Found by: | Date | Description of Finding | Link to screenshot | Target completion date: | Resolved? | Notes
bug | Brendan | 2025-06-23 | typing in keywords "bet," "tuck," and "turn"in the player search result in the app crashing |  |  | yes
suggestion | Brendan | 2025-06-23 | It would be helpful to have the players nicknames/ popular names show up in the player search, not their legal names |  |  | yes
suggestion | Dr. D | 2025-06-23 | for custom players: the input fields should be adjusted- take out runs, clarify IBB vs. BB, take out hits: singles is already a category |  |  | yes
bug | Dr. D | 2025-07-02 | If one doesn't specify the year and team, the "next" button fades out |  |  | yes | A pop-up box was added in order to have the user select the year and team before they can add the player
bug | Dr. D | 2025-07-05 | the metric was now changed to “expected runs per cycle” but the box still says “runs per game” |  |  | yes
bug | Dr. D | 2025-07-05 | the option to limit the number of lefties/righties in a row is no longer there |  |  | yes
suggestion | Dr. D | 2025-07-05 | No “Forgot password” mechanism |  |  | yes
suggestion | Dr. D | 2025-07-05 | It would be great to not have to input the lineup from scratch every time (especially for custom players!). Maybe keep the current players and their stats until I click on a “clear lineup” button? |  |  | yes | "Reuse selections?" checkbox added
suggestion | Dr. D | 2025-07-17 | Find latest Run Expectancy Matrix to use
suggestion | Dr. D | 2025-07-17 | Incorporate multiple RE Matrices (possible fall spin-off)
improvement | Dr. D | 2025-07-20 | "Runs" entry needs to be removed from Custom Player pop-up box
suggestion | Dr. D | 2025-07-20 | Small sample size adjustment |  |  |  | For players with under 100 Pas, league averages could be used, or league averages minus 20%
suggestion | Dr. D | 2025-07-20 | Time interval for player stats